## Sheet1
Risk ID | Description | Likelihood | Impact | Mitigation
R-001 | MongoDB connection fails | Medium | High | Ensure local MongoDB or Atlas connection is configured and accessible
R-002 | Frontend form validation missing | Low | Medium | Implement React validators, test in Selenium
R-003 | API endpoint errors | Medium | High | Automated API testing, logging errors
R-004 | CI/CD workflow fails | Low | Medium | Validate workflow before push, add debugging steps
R-005 | Selenium test flakiness | Medium | Medium | Add proper waits, retry logic, and stable locators